## Erik Kim
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Erik Kim
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Create tasks within the to-do list | 2020-12-02 | 2020-12-12 |  | Ten
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | JDBC Library | 2020-12-03 | 2020-12-05 |  | Three
100% | Create power point slides | 2020-12-10 | 2020-12-10 |  | One
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
0%
`

## Harjit Liyal
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Harjit Liyal
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Do Meeting Notes | 2020-12-02 | 2020-12-12 |  | Ten
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | Create power point slides | 2020-12-10 | 2020-12-10 |  | One
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
0%
`

## Jamil Kocacal
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Jamil Kocacal
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Create tasks within the to-do list | 2020-12-02 | 2020-12-12 |  | Ten
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | Create power point slides | 2020-12-10 | 2020-12-10 |  | One
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
0% | Follow-up
`

## Danny Kong
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Danny Kong
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | Help set up slides for the power point | 2020-12-08 | 2020-12-10 |  | Three
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
0%
`

## Jonathan Eng
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Jonathan Eng
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | Help set up slides for the power point | 2020-12-08 | 2020-12-10 |  | Three
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
100% | Helping with power point annotation | 2020-12-10 | 2020-12-12 |  | Three
0%
`

## Haibo Liu
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Haibo Liu
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | Help set up slides for the power point | 2020-12-08 | 2020-12-10 |  | Three
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
0%
`

## Marlon Louis
To-do list
To be completed by: |  | 2020-12-13 |  | Name: Marlon Louis
Deadline: |  | 2020-12-13 |  | Date: 12/1/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-12-01 | 2020-12-01 |  | One
100% | Update project planner | 2020-12-02 | 2020-12-12 |  | Ten
100% | Questions for Heller | 2020-12-02 | 2020-12-04 | 2020-12-05 | Three | Professor Heller changed project specifications
100% | Pick Queries+tables | 2020-12-02 | 2020-12-03 |  | Two
100% | Finish all queries | 2020-12-03 | 2020-12-10 |  | Seven
100% | Create power point slides | 2020-12-10 | 2020-12-10 |  | One
100% | Normal Power Point Recording | 2020-12-10 | 2020-12-11 |  | Two
100% | Finish all recordings. | 2020-12-10 | 2020-12-12 |  | Three
0% | Follow-up