## Project Planner
Project 2 Group-4 Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | Actual Duration | PERCENT COMPLETE | DAYS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
*Assign tasks and roles to each member | 1 | 1 | 1 | 1 | 100%
*Gather all files and resources needed | 1 | 1 | 1 | 1 | 100%
*Create needed tables. | 2 | 3 | 2 | 2 | 100%
*Ask Questions for better understanding. | 3 | 1 | 3 | 3 | 100%
*Distribute procedures to all group members. | 5 | 1 | 5 | 1 | 100%
*Each member complete their stored procedures. | 5 | 2 | 5 | 4 | 100%
*Update stored procedures to meet project specs. | 9 | 2 | 9 | 2 | 100%
*Test to assure all stored procedures work. | 10 | 2 | 10 | 3 | 100%
*Discuss the JDBC implementation | 11 | 1 | 11 | 1 | 100%
*Complete the JDBC portion | 11 | 4 | 11 | 4 | 100%
*Discuss the layout and outline of the PowerPoints | 13 | 1 | 13 | 1 | 100%
*Complete SQLDoc portion to add into presentation | 13 | 1 | 13 | 1 | 100%
*Create powerpoints and have all members add in their slides | 13 | 3 | 13 | 3 | 100%
*Add audio to slides and complete both Power Points | 16 | 1 | 16 | 1 | 100%