## Erik Kim
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Erik Kim
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare questions for professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Create chosen stored procedures | 2020-11-10 | 2020-11-15 |  | Five
100% | create sequence objects | 2020-11-10 | 2020-11-14 |  | Four
100% | Update JDBC library | 2020-11-10 | 2020-11-14 |  | Four
100% | Power point recordings about program life cycle and procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
100% | Check Everything is Complete | 2020-11-18 | 2020-11-20 |  | Two
0%
`

## Harjit Liyal
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Harjit Liyal
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Create meeting notes and take attendance for each meeting | 2020-11-05 | 2020-11-19 |  | Fifteen
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare Questions for Professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Create showtablerowcount and dimmartial status | 2020-11-10 | 2020-11-15 |  | Five
100% | Create power point slides | 2020-11-15 | 2020-11-16 |  | One
100% | Power point recordings about The meeting notes and stored procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
0%
`

## Jamil Kocacal
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Jamil Kocacal
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Create tasks within the to-do list | 2020-11-05 | 2020-11-19 |  | Fifteen
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare questions for professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Create dimproduct and data stored procedure | 2020-11-10 | 2020-11-15 | 2020-11-16 | Five | Extended due to misunderstanding on load data procedure
100% | Create power point slides | 2020-11-15 | 2020-11-16 |  | One
100% | Power point recordings about To-do list and procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
0%
`

## Danny Kong
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Danny Kong
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare Questions for Professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Create dim territory and sales manager procedure | 2020-11-10 | 2020-11-15 |  | Five
100% | Set up slides for the two power point | 2020-11-15 | 2020-11-15 |  | One
100% | Create power point slides | 2020-11-15 | 2020-11-16 |  | One
100% | Power point recordings about program life cycle and procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
0%
`

## Jonathan Eng
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Jonathan Eng
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare Questions for Professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Create dim product category and dim product sub category procedures | 2020-11-10 | 2020-11-15 |  | Five
100% | Create power point slides | 2020-11-15 | 2020-11-16 |  | One
100% | Power point recordings about program life cycle and procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
0%
`

## Haibo Liu
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Haibo Liu
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare Questions for Professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Create dim order date and dim occupation | 2020-11-10 | 2020-11-15 |  | Five
100% | Create power point slides | 2020-11-15 | 2020-11-16 |  | One
100% | Power point recordings about program life cycle and procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
0%
`

## Marlon Louis
To-do list
To be completed by: |  | 2020-11-20 |  | Name: Marlon Louis
Deadline: |  | 2020-11-20 |  | Date: 11/5/2020
Project 2
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-11-05 | 2020-11-05 |  | One
100% | Complete Project Planner | 2020-11-05 | 2020-11-15 |  | Fifteen
100% | Setup bak file in ssms | 2020-11-05 | 2020-11-07 |  | Two
100% | Prepare Questions for Professor Heller | 2020-11-07 | 2020-11-10 |  | Three
100% | Created dim gender and dim customer procedures | 2020-11-10 | 2020-11-15 |  | Five
100% | Create power point slides | 2020-11-15 | 2020-11-16 |  | One
100% | Power point recordings about program life cycle and procedures | 2020-11-16 | 2020-11-19 |  | Three
100% | JDBC Recording | 2020-11-16 | 2020-11-19 |  | Three
0%
`