## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
Task | Day Start | Amount of Days Planned | Start Day | Days it took | PERCENT COMPLETE | Days
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
First Meet. Discuss the Assignment & Nominated Leader. Assign jobs to group members (Missing 1 Member Until Otherwise Noted)* | 1 | 1 | 1 | 1 | 100%
Assign Task 1 to Each Group Member Finalize Roles for each group member (Task 1: 5 Simple Queries By Next Meet) | 1 | 4 | 1 | 4 | 100%
Check Each Others 5 Queries (Made sure no Queries are too Similar) | 5 | 1 | 5 | 1 | 100%
Assign Task 2 to Each Group Member (Task 2: 7 Medium Queries by Next Meet) | 5 | 5 | 5 | 5 | 100%
Check Each Other 7 Medium Queries (Made sure no Queries were too Similar) (Last Member Joined)* | 10 | 1 | 10 | 1 | 100%
Assign Task 3 to Each Group Member (Task 3: Finish remaining Queries) | 10 | 7 | 10 | 7 | 100%
Discuss and Work on JDBC | 10 | 7 | 10 | 11 | 100%
Discuss Diagram Layout and JSON and assign Task 4 (Task 4: Write Word Document of Queries/Diagrams, Prepare Recordings | 17 | 1 | 17 | 1 | 100%
Discuss JSON and SQL Diagrams; Assign Task 5 (Task 5: Work On Individual Word Submissions of Code Documentation) | 18 | 3 | 18 | 3 | 100%
Continue Fixing JDBC Prepare Powerpoint Presentation Outline | 21 | 1 | 21 | 1 | 100%
Gather All Word Documents Continue Powerpoints Finalize SQL Queries | 22 | 1 | 22 | 1 | 100%
Collect SQL Queries Finalized JDBC Completed Powerpoint Assign Task 6: (Task 6: Record Powerpoint video, and JDBC Video) [Final Task] | 23 | 3 | 23 | 3 | 100%