## Erik Kim
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Erik Kim
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-10-02 | 2020-10-02 |  | One
100% | 5 queries | 2020-10-02 | 2020-10-05 |  | Three
100% | Medium queries | 2020-10-05 | 2020-10-09 |  | Four
100% | Finish Microsoft Word Document | 2020-10-09 | 2020-10-22 |  | Thirteen
100% | Finish all queries | 2020-10-09 | 2020-10-16 |  | Seven
100% | JDBC Library | 2020-10-10 | 2020-10-14 |  | Four
100% | Finish recording individual portion | 2020-10-16 | 2020-10-19 |  | Three
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Two | extended to meet Professor Heller's Standards in the previous meeting
100% | Check Everything is Complete | 2020-10-22 | 2020-10-23 |  | One
0%
`

## Harjit Liyal
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Harjit Liyal
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-10-02 | 2020-10-02 |  | One
100% | Create meeting notes and take attendance for each meeting | 2020-10-02 | 2020-10-23 |  | Twenty-One
100% | 5 queries | 2020-10-02 | 2020-10-05 |  | Three
100% | Medium queries | 2020-10-05 | 2020-10-09 |  | Four
100% | Finish all queries | 2020-10-09 | 2020-10-16 |  | Seven
100% | Finish Microsoft Word Document | 2020-10-09 | 2020-10-22 |  | Thirteen
100% | Finish recording portions individual portion | 2020-10-16 | 2020-10-19 |  | Three
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Two | extended to meet Professor Heller's Standards in the previous meeting
0%
`

## Jamil Kocacal
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Jamil Kocacal
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-10-02 | 2020-10-02 |  | One
100% | Create tasks within the to-do list | 2020-10-02 | 2020-10-23 |  | Twenty-One
100% | 5 queries | 2020-10-02 | 2020-10-05 |  | Three
100% | Medium queries | 2020-10-05 | 2020-10-09 |  | Four
100% | Finish all queries | 2020-10-09 | 2020-10-16 |  | Seven
100% | Finish Microsoft Word Document | 2020-10-09 | 2020-10-22 |  | Thirteen
100% | Finish recording Individual Portion | 2020-10-16 | 2020-10-19 |  | Three
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Two | extended to meet Professor Heller's Standards in the previous meeting
0% | Follow-up
`

## Danny Kong
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Danny Kong
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-10-02 | 2020-10-02 |  | One
100% | 5 queries | 2020-10-02 | 2020-10-05 |  | Three
100% | Medium queries | 2020-10-05 | 2020-10-09 |  | Four
100% | Finish all queries | 2020-10-09 | 2020-10-16 |  | Seven
100% | Help set up slides for the power point | 2020-10-10 | 2020-10-23 |  | Thirteeen
100% | Finish recording Individual Portion | 2020-10-16 | 2020-10-19 |  | Three
100% | Finish Microsoft Word Document | 2020-10-09 | 2020-10-22 |  | Thirteen
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Two | extended to meet Professor Heller's Standards in the previous meeting
0%
`

## Jonathan Eng
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Jonathan Eng
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Planning | 2020-10-02 | 2020-10-02 |  | One
100% | Complete Project Planner | 2020-10-02 | 2020-10-23 |  | Twenty-One
100% | 5 queries | 2020-10-02 | 2020-10-05 |  | Three
100% | Medium queries | 2020-10-05 | 2020-10-09 |  | Four
100% | Finish all queries | 2020-10-09 | 2020-10-16 |  | Seven
100% | Finish Microsoft Word Document | 2020-10-09 | 2020-10-22 |  | Thirteen
100% | Finish recording Individual Portion | 2020-10-16 | 2020-10-19 |  | Three
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Five | extended to meet Professor Heller's standards in the previous meeting
100% | Edit JDBC Recording | 2020-10-21 | 2020-10-22 | 2020-10-23 | Three | Extended due to needing to redo the recording and thus need to reedit to meet Professor Heller's standard.
0%
`

## Haibo Liu
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Haibo Liu
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | 5 queries | 2020-10-05 | 2020-10-05 | 2020-10-07 | Three | Joined group late required more time to finish five queries
100% | Medium queries | 2020-10-05 | 2020-10-09 |  | Four
100% | Finish all queries | 2020-10-09 | 2020-10-16 |  | Seven
100% | Finish Microsoft Word Document | 2020-10-09 | 2020-10-22 |  | Thirteen
100% | Help set up slides for the power point | 2020-10-10 | 2020-10-23 |  | Thirteen
100% | Finish recording Individual Portion | 2020-10-16 | 2020-10-19 |  | Three
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Five | extended to meet Professor Heller's standards in the previous meeting
0%
`

## Marlon Louis
To-do list
To be completed by: |  | 2020-10-25 |  | Name: Marlon Louis
Deadline: |  | 2020-10-25 |  | Date: 10/2/2020
Project 1
% done | Phase | Start By | Original Due By | Revised Due By | Number Of Days | Revision Notes
100% | Catch up on queries | 2020-10-13 | 2020-10-16 | 2020-10-18 | Five | Joined group late needed more time to finish all the queries
100% | Finish Microsoft Word Document | 2020-10-16 | 2020-10-22 |  | Thirteen
100% | Record Beginning Segment of the power point | 2020-10-16 | 2020-10-23 |  | Seven
100% | Finish recording Individual Portion | 2020-10-16 | 2020-10-19 |  | Three
100% | JDBC Recording | 2020-10-16 | 2020-10-21 | 2020-10-22 | Five | extended to meet Professor Heller's standards in the previous meeting
0%
`